## Week 2
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-03-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-03-07 | 8:00 | 12:00 | 4:00 | Researching about modern backend frameworks used for web development | Picking up the correct framework for the project is a very important task so an in-depth research is necessary. | Taking into account the experience of the team and the project requirements, we are leaning towards Django because it is suitable for development of large applications and suitable for beginner developers.
Sunday | 2021-03-07 | 14:00 | 16:00 | 2:00 | Preparing the templates for Meeting minutes and Agenda | Meeting minutes and Agenda are part of the course assessment. Therefore, a well-presented template for these documents will help the team members who are in charge of preparing them easily fill in the contents. | To make sure that everyone else is aware of the templates to be used.
Sunday | 2021-03-07 | 21:00 | 22:00 | 1:00 | Attending 2nd internal team meeting | The meeting was the time that we shared with each other the findings from our research on web development frameworks and to get prepared for the 1st client meeting. | To bring up all the questions that we came across after our internal meeting to the 1st client meeting.
Tuesday | 2021-03-09 | 16:00 | 17:00 | 1:00 | Attending 2nd MCI workshop | The workshop taught me necessary skills to do a pitch presentation, which is part of the course assessment. | To apply the skills learnt for the pitch presentation
Wednesday | 2021-03-10 | 10:00 | 11:00 | 1:00 | Attending 1st client meeting | I got to know the client and their project requirements after the meeting. | After this kick-off meeting, we were clearer about what we had to do for the project.
Wednesday | 2021-03-10 | 21:00 | 22:30 | 1:30 | Attending 3rd internal team meeting | The meeting helped us to recap what was discussed during the client meeting and planned the tasks for the team. | Every member was on the same page about the project requirements and what to do next.
Wednesday | 2021-03-10 | 22:30 | 0:30 | 2:00 | Preparing meeting minutes for the 1st client meeting | The meeting minutes provide us with a written record of what was discussed and agreed at a meeting, so we will have the same recollections from the meeting and the same ideas about what was agreed. It is also part of the course assessment. | To send the meeting minutes for review before sending them to all attendees and uploading them to GitHub
Thursday | 2021-03-11 | 9:30 | 10:00 | 0:30 | Sending meeting minutes to all attendees and Uploading the meeting minutes to GitHub | By sending the minutes to the client, it may help to identify confusing items early if the client finds our summary to be incorrect. This saves times and effort. | The meeting minutes were sent and uploaded to GitHub.
Thursday | 2021-03-11 | 10:00 | 10:30 | 0:30 | Using the boilerplate to run the test map | The boilerplate gave me a sense of how our future product would look like and provided me with a chance to get familiarised with GItHub. | I could run the app in the development mode succesfully and the map was loaded.
Thursday | 2021-03-11 | 13:30 | 17:30 | 4:00 | Studying ReactJS (https://www.linkedin.com/learning/learning-react-js-5/using-create-react-app?u=79987266) and Setting up Django in my laptop | ReactJS and Django are the two frameworks that we are planning to use for our platform so this is the first step for me to get familiarised with these frameworks. | - Studying ReactJS: completed with setting up Node.js and learnt some basic functions of ReactJS. - Django setup: completed
Friday | 2021-03-12 | 20:00 | 22:00 | 2:00 | Preparing agenda for the 2nd client meeting | The agenda sets clear expectations for all attendees what needs to occur during the meeting. It helps team members prepare, allocates time wisely, quickly gets everyone on the same topic, and identifies when the discussion is complete. It is also part of the course assessment. | To send the agenda for review before sending them to all meeting attendees (at least one day before the next client meeting next Monday) and uploading them to GitHub.
Saturday | 2021-03-13 | 9:30 | 10:00 | 0:30 | Sending agenda for the 2nd client meeting to all attendees and Uploading the agenda to GitHub | By sending the agenda to the client, it may help to get the client prepared for the upcoming meeting. | The agenda were sent and uploaded to GitHub.
Saturday | 2021-03-13 | 10:00 | 16:00 | 6:00 | Studying Django (https://www.linkedin.com/learning/learning-django-2/rapidly-create-web-applications?u=79987266) | For backend environment of this project, we use Django so getting familiar with it will help me to handle backend tasks coming up. | I learnt about Django project, app, migrations, architecture and some common commands used for Django
Saturday | 2021-03-13 | 16:00 | 17:00 | 1:00 | Preparing timesheet for week 2 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 3
|  |  | Total | 27:00

## Week 3
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-03-14
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-03-14 | 21:00 | 22:00 | 1:00 | Attending the 4th internal team meeting | The meeting was the time that we shared with each other the findings from doing our tasks and planned the tasks for the coming week. | To get prepared for our 2nd client meeting.
Monday | 2021-03-15 | 10:00 | 11:00 | 1:00 | Attending the 2nd client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-03-15 | 15:00 | 17:00 | 2:00 | Watching lecture | I learnt about what to prepare for the pitch presentation, business case and project plan. | To apply what the lecturer taught us to our pitch presentation, business case and project plan.
Tuesday | 2021-03-16 | 9:00 | 9:30 | 0:30 | Reviewing the meeting minutes for the 2nd client meeting | The meeting minutes is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The meeting minutes is finalised before it's sent out and submitted.
Tuesday | 2021-03-16 | 14:00 | 16:00 | 2:00 | Research about Database (NoSQL, SQL, others) | It was highlighted by the client that we need to find a suitable database to use for the project. | To find out which type of database can suit the client's needs and the project team capabilities the most.
Tuesday | 2021-03-16 | 16:00 | 17:00 | 1:00 | Attending the 2nd MCI workshop | The workshop taught me necessary skills to do the first milestone report, which is part of the course assessment, and to use GitHub. | To apply the skills learnt for the first milestone report and using GitHub for coding collaboration.
Wednesday | 2021-03-17 | 21:00 | 21:30 | 0:30 | Using the boilerplate to run the backend setup | The boilerplate gave me a sense of how our future product would look like. | I could run the app in the development mode succesfully and the webpage was loaded.
Wednesday | 2021-03-17 | 22:00 | 23:00 | 1:00 | Attending the 5th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the rest of the week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-03-20 | 9:00 | 15:00 | 6:00 | Setting up a temporary database (SQL) | Database is the key point that connects our backend and frontend so it is very important for the project. | A temporary database is set up for testing purpose.
Saturday | 2021-03-20 | 16:00 | 18:00 | 2:00 | Finalising the research findings for presentation during the next client meeting | It was highlighted by the client that we need to decide on which database to use for the project. | To present my findings to the client during the next client meeting.
Saturday | 2021-03-20 | 22:00 | 23:00 | 1:00 | Attending the 6th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-03-20 | 23:00 | 0:00 | 1:00 | Preparing timesheet for week 2 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 4
|  |  | Total | 19:00

## Week 4
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-03-21
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-03-21 | 9:00 | 17:00 | 8:00 | Re-designing the database structure | Database is the key point that connects our backend and frontend so it is very important for the project. | To present about our system's database structure to the client in the next meeting
Sunday | 2021-03-21 | 22:00 | 23:00 | 1:00 | Attending the 7th internal team meeting | The meeting was the time that we shared with each other the findings from doing our tasks and planned the tasks for the coming week. | To get prepared for our 3rd client meeting.
Sunday | 2021-03-21 | 23:00 | 1:00 | 2:00 | Preparing the draft pitch presentation slides | The pitch presentation is part of the course assessment. | To present the draft slides to the clients for feedbacks.
Monday | 2021-03-22 | 10:00 | 11:00 | 1:00 | Attending the 3rd client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-03-22 | 11:00 | 12:00 | 1:00 | Attending the 8th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-03-22 | 15:00 | 16:00 | 1:00 | Watching lecture | I learnt about what to prepare for the pitch presentation, business case and project plan. | To apply what the lecturer taught us to our pitch presentation, business case and project plan.
Monday | 2021-03-22 | 20:00 | 23:00 | 3:00 | Discussing with Thanh and Jon to clarify about Thanh's assigned task on the map filter | We tried to clear the backlog before moving on with other tasks | We figured out how to work more effectively as a team.
Tuesday | 2021-03-23 | 13:30 | 14:00 | 0:30 | Reviewing the meeting minutes for the 3rd client meeting | The meeting minutes is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The meeting minutes is finalised before it's sent out and submitted.
Tuesday | 2021-03-23 | 14:00 | 16:00 | 2:00 | Working with Thanh to prepare the UML diagram for database design | It was highlighted by the client during the meeting that we need to have a diagram for database design to help with the database implementation and maintenance. | To continue helping Thanh to come up with the finalised UML diagram for database design when needed.
Tuesday | 2021-03-23 | 16:00 | 16:15 | 0:15 | Attending the MCI workshop | During the workshop I was able to clear my doubts about the pitch presentation requirements | To apply the knowledge gained for the pitch presentation.
Tuesday | 2021-03-23 | 16:30 | 17:30 | 1:00 | Preparing the draft first milestone plan | The first milestone report is part of the course assessment | To present the draft first milestone plan to the team for discussion
Tuesday | 2021-03-23 | 20:00 | 22:00 | 2:00 | Reading the reference documents provided by the client for pitch presentation preparation | The pitch presentation requires us to explain what the problem is, why we need to solve the problem and the references give us lots of background knowledge to answer these questions | To refer to the reference documents for our pitch presentation
Tuesday | 2021-03-23 | 22:00 | 0:00 | 2:00 | Preparing the draft pitch presentation slides | Preparing the draft pitch presentation slides gave me some ideas on how to structure the presentation and divide the tasks among the teammates. | To present the draft pitch slides to the team during the internal meeting and submit to MyUni for the lecturer's feedbacks.
Wednesday | 2021-03-24 | 22:00 | 23:30 | 1:30 | Attending the 9th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the rest of the week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-03-27 | 10:00 | 18:00 | 8:00 | Researching, Preparing and Revising the pitch presentation slides | The pitch presentation slides are the main tool for us to introduce our project and show how important it is to the listeners | To present the slides to the team during the internal team meeting
Saturday | 2021-03-27 | 22:00 | 23:30 | 1:30 | Attending the 10th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-03-27 | 23:30 | 0:30 | 1:00 | Preparing timesheet for week 4 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 5
|  |  | Total | 36:45

## Week 5
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-03-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2021-03-29 | 10:00 | 11:00 | 1:00 | Attending the 4th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-03-29 | 11:00 | 13:00 | 2:00 | Attending the 11th internal team meeting | We reviewed our 1st milestone plan and rehearsed for the pitch presentation. | We got ourselves prepared for the actual pitch presentation recording the next day and for the business case & draft plan submission by the end of the week.
Monday | 2021-03-29 | 16:00 | 17:00 | 1:00 | Watching lecture | I learnt about what to prepare for the pitch presentation, business case and project plan. | To apply what the lecturer taught us to our pitch presentation, business case and project plan.
Tuesday | 2021-03-30 | 10:00 | 13:00 | 3:00 | Recording the pitch presentation | The pitch presentation is part of the course assessment. | To finalise the recorded videos before submission
Wednesday | 2021-03-31 | 20:00 | 20:30 | 0:30 | Reviewing the finalised pitch presentation video | The pitch presentation is part of the course assessment. | We submitted the pitch presentation video link before deadline.
Thursday | 2021-04-01 | 10:00 | 16:00 | 6:00 | Preparing the business case and draft plan | The busines case and draft plan is part of the course assessment. | To present the results to the team during the team meeting
Thursday | 2021-04-01 | 22:00 | 23:00 | 1:00 | Attending the 12th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the next tasks. | Every member was on the same page about the project requirements and what to do next.
Friday | 2021-04-02 | 19:00 | 23:00 | 4:00 | Revising the business case and draft plan as per the comments from the team | The busines case and draft plan is part of the course assessment. | To present the results to the team during the team meeting
Saturday | 2021-04-03 | 22:00 | 23:00 | 1:00 | Attending the 13th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-04-03 | 23:00 | 0:00 | 1:00 | Preparing timesheet for week 5 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 6
|  |  | Total | 20:30

## Week 6
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-04-04
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-04-04 | 10:00 | 11:00 | 1:00 | Finalising the Business Case and Draft Plan for submission | The busines case and draft plan is part of the course assessment. | The busines case and draft plan were submitted before deadline.
Sunday | 2021-04-04 | 11:00 | 11:30 | 0:30 | Preparing agenda for the 5th client meeting | The agenda sets clear expectations for all attendees what needs to occur during the meeting. It helps team members prepare, allocates time wisely, quickly gets everyone on the same topic, and identifies when the discussion is complete. It is also part of the course assessment. | To send the agenda for review before sending them to all meeting attendees (at least one day before the next client meeting next Monday) and uploading them to GitHub.
Sunday | 2021-04-04 | 11:30 | 11:45 | 0:15 | Sending agenda for the 5th client meeting to all attendees and Uploading the agenda to GitHub | By sending the agenda to the client, it may help to get the client prepared for the upcoming meeting. | The agenda were sent and uploaded to GitHub.
Tuesday | 2021-04-06 | 10:00 | 11:00 | 1:00 | Attending the 5th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Tuesday | 2021-04-06 | 11:00 | 11:30 | 0:30 | Attending the 14th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Tuesday | 2021-04-06 | 14:00 | 14:30 | 0:30 | Preparing meeting minutes for the 5th client meeting | The meeting minutes provide us with a written record of what was discussed and agreed at a meeting, so we will have the same recollections from the meeting and the same ideas about what was agreed. It is also part of the course assessment. | To send the meeting minutes for review before sending them to all attendees and uploading them to GitHub
Tuesday | 2021-04-06 | 16:00 | 17:00 | 1:00 | Attending the MCI workshop | During the workshop, I was informed of the tasks to do for the pitch discussion. I also learnt about the learning moods that we might have a long the project. The workshop also gave me some ideas on how to do the first milestone report, which is part of the course assessment. | To watch the pitch presentations of other teams and come up with questions as well as answers for other teams. I also learnt to embrace all the different moods during the project to move forward. Also to apply the information gained for the first milestone report preparation.
Tuesday | 2021-04-06 | 18:00 | 18:15 | 0:15 | Sending meeting minutes to all attendees and Uploading the meeting minutes to GitHub | By sending the minutes to the client, it may help to identify confusing items early if the client finds our summary to be incorrect. This saves times and effort. | The meeting minutes were sent and uploaded to GitHub.
Tuesday | 2021-04-06 | 19:00 | 23:00 | 4:00 | Watching pitch presentations of other teams and raising questions | Making questions contributes to our mark for the pitch. | To discuss with the team about the proposed questions.
Wednesday | 2021-04-07 | 20:00 | 20:30 | 0:30 | Finalising the questions for the pitch presentations and posting them to the discussion board | Making questions contributes to our mark for the pitch. | All questions were posted on the discussion board.
Thursday | 2021-04-08 | 10:00 | 16:00 | 6:00 | Preparing the project architecture and class diagram | Project architecture and class diagram is one of the activities of our 1st milestone. | To discuss with the team about the proposed project architecture and class diagram.
Thursday | 2021-04-08 | 16:00 | 17:00 | 1:00 | Preparing the draft answers for the pitch questions | Answering questions contributes to our mark for the pitch. | To discuss with the team about the proposed answers.
Thursday | 2021-04-08 | 22:00 | 0:00 | 2:00 | Attending the 15th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the next tasks. | Every member was on the same page about the project requirements and what to do next.
Friday | 2021-04-09 | 0:00 | 0:30 | 0:30 | Posting the answers for the first batch of pitch questions | Answering questions contributes to our mark for the pitch. | The first batch of answers was posted on the discussion board.
Friday | 2021-04-09 | 22:00 | 23:00 | 1:00 | Finalising and posting the answers for the second batch of pitch questions | Answering questions contributes to our mark for the pitch. | The second batch of answers was posted on the discussion board before deadline.
Saturday | 2021-04-10 | 10:00 | 10:30 | 0:30 | Revising the templates for meeting minutes and agenda in accordance with the tutor's recommendations. | Meeting minutes and Agenda are part of the course assessment. Therefore, well-presented templates for these documents will help the team members who are in charge of preparing them easily fill in the contents. | To make sure that everyone else is aware of the templates to be used.
Saturday | 2021-04-10 | 10:30 | 12:00 | 1:30 | Revising the project architecture and class diagram | Project architecture and class diagram is one of the activities of our 1st milestone. | To discuss with the team about the revised project architecture and class diagram.
Saturday | 2021-04-10 | 13:00 | 14:00 | 1:00 | Preparing for Milestone 1 report | Milestone 1 report is part of the course assessment | To discuss with the team about the proposed Milestone 1 report's actual results of activities.
Saturday | 2021-04-10 | 14:00 | 15:00 | 1:00 | Preparing list of activities for Milestone 2 | Final report is part of the course assessment so we need to come up with the list of activities for the milestone 2. | To discuss with the team about the proposed Milestone 2's list of activities.
Saturday | 2021-04-10 | 22:00 | 0:00 | 2:00 | Attending the 16th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-04-10 | 0:00 | 1:00 | 1:00 | Preparing timesheet for week 6 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 7
|  |  | Total | 27:00

## 2-week mid-term break
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-04-11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-04-11 | 10:00 | 11:00 | 1:00 | Revising the project architecture and class diagram & Rehearsing for the presentation | Project architecture and class diagram is one of the activities of our 1st milestone. | To present the project architecture and class diagram during the next client meeting.
Monday | 2021-04-12 | 10:00 | 11:00 | 1:00 | Attending the 6th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-04-12 | 11:00 | 11:30 | 0:30 | Attending the 17th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-04-12 | 20:00 | 0:00 | 4:00 | Researching backend-frontend (Django-React) integration | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Completed the 2 online couses on LinkedIn Learning to understand the integration concepts: https://www.linkedin.com/learning/building-react-and-django-apps/creating-a-viewset-with-django?u=79987266 and https://www.linkedin.com/learning/building-restful-web-apis-with-django/create-a-rest-api-with-django-and-django-rest-framework?u=79987266
Tuesday | 2021-04-13 | 12:00 | 22:00 | 10:00 | Setting up backend-frontend (Django-React) integration | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Managed to set up the API using Django REST framework for Django to push data out.
Wednesday | 2021-04-14 | 19:00 | 22:00 | 3:00 | Restructuring of the project code to follow the project architecture | This is a preparation step for the milestone 1 submission | Committed the new code changes to a new branch called "Integration"
Wednesday | 2021-04-14 | 22:00 | 23:30 | 1:30 | Attending the 18th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-04-15 | 12:00 | 22:00 | 10:00 | Setting up backend-frontend (Django-React) integration (cont.) | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Managed to get React to retrieve data from the API using Django REST framework.
Saturday | 2021-04-17 | 12:00 | 16:00 | 4:00 | Researching and Preparing slides for integration architecture approaches | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | To present the approaches during the internal team meeting to get feedbacks before presenting them during the client meeting.
Saturday | 2021-04-17 | 22:00 | 0:00 | 2:00 | Attending the 19th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Sunday | 2021-04-18 | 10:00 | 10:30 | 0:30 | Reviewing and Revising the agenda for Jon to submit | The agenda is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The agenda is finalised before it's sent out and submitted.
Monday | 2021-04-19 | 10:00 | 11:00 | 1:00 | Attending the 7th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-04-19 | 11:00 | 11:30 | 0:30 | Attending the 20th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-04-19 | 20:00 | 20:30 | 0:30 | Reviewing and Revising the meeting minutes for Thanh to submit | The meeting minutes is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The meeting minutes is finalised before it's sent out and submitted.
Monday | 2021-04-19 | 20:30 | 0:30 | 4:00 | Researching the integration approach React-Express-SQLite to compare with the Django REST API approach | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | After the research we decided not to go for this approach due to the complication in maintaining 3 servers for Django, React and Express.
Tuesday | 2021-04-20 | 10:00 | 12:00 | 2:00 | Fixing the bugs with the integration setup | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Not all the bugs were fixed. To discuss with the team during the internal team meeting to find out what went wrong
Tuesday | 2021-04-20 | 13:00 | 17:00 | 4:00 | Preparing Milestone 1 report | Milestone 1 report is part of the course assessment | To present the report during the next internal team meeting
Wednesday | 2021-04-21 | 22:00 | 0:00 | 2:00 | Attending the 21st internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Wednesday | 2021-04-21 | 0:00 | 2:00 | 2:00 | Fixing the bugs with the integration setup (cont.) | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Got some ideas on what went wrong and would continue working on the bug fix
Friday | 2021-04-23 | 20:00 | 0:00 | 4:00 | Fixing the bugs with the integration setup (cont.) | Integration between frontend and backend is one of the most important tasks of the project which allows the frontend to query data stored in the backend database. It is the first activity of our 2nd milestone that we need to achieve so that other frontend related activities can proceed. | Completed with the integration between backend and frontend.
Saturday | 2021-04-24 | 13:00 | 14:00 | 1:00 | Revising the milestone 1 report based on other team members' comments | Milestone 1 report is part of the course assessment | To finalise the report for submission
Saturday | 2021-04-24 | 14:00 | 16:00 | 2:00 | Finalising the application architecture and database design in preparation for the 1st milestone submission | Application architecture and database design are the two documents we have to provide for the Milestone 1 | To present to the team during the next internal team meeting before submitting to "master" branch on GitHub
Saturday | 2021-04-24 | 16:00 | 17:00 | 1:00 | Preparing timesheet for the 2-week break and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 7
|  |  | Total | 61:30

## Week 7
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-04-25
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-04-25 | 22:00 | 1:00 | 3:00 | Attending the 22nd internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Monday | 2021-04-26 | 10:00 | 10:30 | 0:30 | Reviewing and Revising the agenda for Thanh to submit | The agenda is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The agenda is finalised before it's sent out and submitted.
Monday | 2021-04-26 | 10:30 | 11:00 | 0:30 | Testing the new changes related to displaying the neighbour images on frontend | Displaying the neighbour images on frontend is one of the activities of milestone 2 and is the most important feature of the web app. | New changes are tested thoroughly before being shown to the client.
Tuesday | 2021-04-27 | 10:00 | 11:00 | 1:00 | Attending the 8th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Tuesday | 2021-04-27 | 11:00 | 12:00 | 1:00 | Attending the 23rd internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Tuesday | 2021-04-27 | 16:00 | 17:00 | 1:00 | Attending the MCI workshop | The workshop provided us with more information about the coming assessesment - Testing plan | To prepare a template for the Testing plan
Thursday | 2021-04-29 | 22:00 | 23:00 | 1:00 | Attending the 24th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-04-29 | 23:00 | 0:30 | 1:30 | Revising the milestone 1 report for submission | Milestone 1 report is part of the course assessment | To finalise the report for submission
Friday | 2021-04-30 | 10:00 | 11:00 | 1:00 | Finalising the milestone 1 report for submission | Milestone 1 report is part of the course assessment | The milestone 1 report was submitted and updated on GitHub before the deadline.
Friday | 2021-04-30 | 13:00 | 17:00 | 4:00 | Studying ReactJS | React is the framework used for our frontend. Since the focus of our second milestone is frontend, understanding the framework will help me with frontend-related tasks such as designing data flow diagram, develop a new function, unit testing, bug fixing, etc. for milestone 2 | To continue with the online course https://www.linkedin.com/learning/learning-react-js-5/using-create-react-app?u=79987266
Saturday | 2021-05-01 | 13:00 | 17:00 | 4:00 | Studying ReactJS (cont.) | React is the framework used for our frontend. Since the focus of our second milestone is frontend, understanding the framework will help me with frontend-related tasks such as designing data flow diagram, develop a new function, unit testing, bug fixing, etc. for milestone 2 | Completed with the online course.
Saturday | 2021-05-01 | 22:00 | 0:00 | 2:00 | Attending the 25th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-01 | 0:00 | 1:00 | 1:00 | Preparing timesheet for week 7 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 8
|  |  | Total | 21:30

## Week 8
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-05-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2021-05-03 | 10:00 | 11:00 | 1:00 | Attending the 9th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-05-03 | 11:00 | 12:00 | 1:00 | Attending the 26th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-05-03 | 21:00 | 22:00 | 1:00 | Watching lecture | The lecture gave me some guidelines on the coming assginment requirements for milestone 2 plan | To apply what the lecturer taught us to our milestone 2 plan
Monday | 2021-05-03 | 22:00 | 23:00 | 1:00 | Preparing meeting minutes for the 9th client meeting | The meeting minutes provide us with a written record of what was discussed and agreed at a meeting, so we will have the same recollections from the meeting and the same ideas about what was agreed. It is also part of the course assessment. | To send the meeting minutes for review before sending them to all attendees and uploading them to GitHub
Tuesday | 2021-05-04 | 10:00 | 10:15 | 0:15 | Sending meeting minutes to all attendees and Uploading the meeting minutes to GitHub | By sending the minutes to the client, it may help to identify confusing items early if the client finds our summary to be incorrect. This saves times and effort. | The meeting minutes were sent and uploaded to GitHub.
Tuesday | 2021-05-04 | 10:15 | 11:15 | 1:00 | Revising milestone 2 plan | Milestone 2 plan is part of the course assessment | To discuss with the team during the internal team meeting
Tuesday | 2021-05-04 | 11:00 | 13:00 | 2:00 | Designing UI | Making the frontend user-friendly is one of our goals for milestone 2 | To present the UI design to the team during the internal team meeting
Tuesday | 2021-05-04 | 13:00 | 14:00 | 1:00 | Studying how to publish the website | Publishing the website is one of our milestone 2 activities | To discuss with the team during the internal team meeting
Wednesday | 2021-05-05 | 21:00 | 21:15 | 0:15 | Completing the Team feedback quiz | The team feedback quiz was to reflect how the team are working so far in terms of balanced contributions | Quiz submitted
Wednesday | 2021-05-05 | 21:15 | 21:30 | 0:15 | Revising the UI design | Making the frontend user-friendly is one of our goals for milestone 2 | To present the revised UI design to the team during the internal team meeting
Wednesday | 2021-05-05 | 22:00 | 23:15 | 1:15 | Attending the 27th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-05-05 | 14:00 | 14:30 | 0:30 | Finalising the milestone 2 plan for submission | Milestone 2 plan is part of the course assessment | The milestone 2 plan was submitted before the deadline.
Saturday | 2021-05-08 | 9:00 | 11:00 | 2:00 | Studying how to publish the website (cont.) and Exploring on the libraries to use for frontend | Publishing the website and Making the frontend user-friendly are our goals for milestone 2 | To discuss with the client about publishing the website and share with the team about the libraries for making UI more user-friendly (https://material-ui.com and https://ant.design/components/overview/)
Saturday | 2021-05-08 | 12:00 | 22:00 | 10:00 | Studying & Preparing the Testing plan | Testing plan is part of the course assessment | To discuss with the team during the internal team meeting
Saturday | 2021-05-08 | 22:00 | 23:30 | 1:30 | Attending the 28th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-08 | 23:30 | 0:30 | 1:00 | Preparing timesheet for week 8 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 9
|  |  | Total | 25:00

## Week 9
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-05-09
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2021-05-10 | 10:00 | 11:00 | 1:00 | Attending the 10th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-05-10 | 11:00 | 11:30 | 0:30 | Attending the 29th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-05-10 | 21:00 | 22:00 | 1:00 | Watching lecture | The lecture gave me some ideas on how to plan the tasks for the coming weeks | To plan our tasks accordingly for the coming weeks
Monday | 2021-05-10 | 22:00 | 22:15 | 0:15 | Reviewing and Revising the meeting minutes for Jon to submit | The meeting minutes is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The meeting minutes was finalised before being sent out and submitted.
Tuesday | 2021-05-11 | 8:00 | 13:00 | 5:00 | Preparing the Testing plan | Testing plan is part of the course assessment | To discuss with the team during the internal team meeting
Tuesday | 2021-05-11 | 14:00 | 19:00 | 5:00 | Performing unit tests for Django API views | Unit tests are carried out as part of the testing plan | Completed unit testing for Django API views
Wednesday | 2021-05-12 | 22:00 | 1:00 | 3:00 | Attending the 30th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-05-13 | 10:00 | 20:00 | 10:00 | Researching and Testing to publish the web app via Heroku | Publishing the website is one of the activities of milestone 2 | Hit some errorrs, to continue with the testing
Friday | 2021-05-14 | 20:00 | 0:00 | 4:00 | Researching and Testing to publish the web app via Heroku (cont.) | Publishing the website is one of the activities of milestone 2 | Still hit errors, need to continue with the testing
Saturday | 2021-05-15 | 10:00 | 20:00 | 10:00 | Researching and Testing to publish the web app via Heroku (cont.) | Publishing the website is one of the activities of milestone 2 | Managed to publish the webiste https://mapmanagementplatform-webapp.herokuapp.com/
Saturday | 2021-05-15 | 22:00 | 23:40 | 1:40 | Attending the 31st internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-15 | 23:40 | 0:40 | 1:00 | Preparing timesheet for week 9 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 10
|  |  | Total | 42:25

## Week 10
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-05-16
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-05-16 | 0:00 | 1:00 | 1:00 | Preparing agenda for the 11th client meeting | The agenda sets clear expectations for all attendees what needs to occur during the meeting. It helps team members prepare, allocates time wisely, quickly gets everyone on the same topic, and identifies when the discussion is complete. It is also part of the course assessment. | To send the agenda for review before sending them to all meeting attendees (at least one day before the next client meeting next Monday) and uploading them to GitHub.
Sunday | 2021-05-16 | 9:00 | 9:15 | 0:15 | Sending agenda for the 11th client meeting to all attendees and Uploading the agenda to GitHub | By sending the agenda to the client, it may help to get the client prepared for the upcoming meeting. | The agenda were sent and uploaded to GitHub.
Monday | 2021-05-17 | 10:00 | 11:00 | 1:00 | Attending the 11th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands.
Monday | 2021-05-17 | 11:00 | 11:30 | 0:30 | Attending the Zoom meeting with tutor | The meeting was when we got the feedbacks from the tutor about our project | We were happy with the news that we were one of the best teams in the course and we should do our best to achieve better results
Monday | 2021-05-17 | 11:30 | 12:00 | 0:30 | Attending the 32nd internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-05-17 | 21:00 | 22:00 | 1:00 | Researching Heroku web publication | During the client meeting, we were asked to advise how many Heroku dynos they should use for the project in preparation for publishing the website on Heroku | To discuss with the team during the internal team meeting about the findings
Tuesday | 2021-05-18 | 7:30 | 8:00 | 0:30 | Taking the LinkedIn Learning course on Testing React to prepare for the testing plan | Testing plan is part of the course assessment | Completed the course https://www.linkedin.com/learning/react-testing-and-debugging/
Tuesday | 2021-05-18 | 8:00 | 8:15 | 0:15 | Reviewing the meeting minutes for Thanh to submit | The meeting minutes is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The meeting minutes was finalised before being sent out and submitted.
Tuesday | 2021-05-18 | 8:15 | 8:45 | 0:30 | Testing the scheduler function for a new region Hanoi | During the unit testing process, we realized that the scheduler function had a bug that need fixing | The scheduler function worked well after the fix.
Tuesday | 2021-05-18 | 8:45 | 13:00 | 4:15 | Performing unit tests for serializers | Unit tests are carried out as part of the testing plan, which is one of the course assessments | Still hit errors, need to continue with the testing
Tuesday | 2021-05-18 | 16:00 | 17:00 | 1:00 | Attending the MCI workshop | The workshop provided us with information about how to design UI/UX | To apply the knowledge gained to make our project's website UI more user-friendly.
Tuesday | 2021-05-18 | 19:00 | 0:00 | 5:00 | Performing unit tests for serializers (cont.) | Unit tests are carried out as part of the testing plan, which is one of the course assessments | Still hit errors, need to continue with the testing
Wednesday | 2021-05-19 | 19:00 | 21:00 | 2:00 | Performing unit tests for serializers (cont.) | Unit tests are carried out as part of the testing plan, which is one of the course assessments | Completed unit testing for serializers
Wednesday | 2021-05-19 | 22:00 | 0:00 | 2:00 | Attending the 33rd internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-05-20 | 10:00 | 20:00 | 10:00 | Perfoming unit tests for Django REST API - React integration | Integration tests are carried out as part of the testing plan, which is one of the course assessments | Completed unit testing for Django REST API - React integration
Friday | 2021-05-21 | 20:00 | 21:00 | 1:00 | Perfoming release testing for frontend function: Selecting an image point | Release tests are carried out as part of the testing plan, which is one of the course assessments | Found a bug that the point was not highlighted because it was actually referring to sequence and informed team
Saturday | 2021-05-22 | 10:00 | 17:00 | 7:00 | Finalising the testing plan | Testing plan is part of the course assessment | To discuss with the team during the internal team meeting and ask for review
Saturday | 2021-05-22 | 22:00 | 23:15 | 1:15 | Attending the 34th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-22 | 23:15 | 0:15 | 1:00 | Preparing timesheet for week 10 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 11
|  |  | Total | 40:00

## Week 11
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-05-23
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Sunday | 2021-05-23 | 10:00 | 10:15 | 0:15 | Reviewing and Revising the agenda for Thanh to submit | The agenda is part of the course assessment and sent to the client so we need to make sure that it is well-presented. | The agenda is finalised before it's sent out and submitted. This is in fact our last agenda for the project since there is no more client meeting.
Sunday | 2021-05-23 | 10:15 | 12:15 | 2:00 | Preparing templates for technical specifications and user guide documents | Technical specifications and user guide documents are the documentation that we have to deliver to the client in milestone 2 | To discuss with the team during the internal team meeting about the task allocation for the documents
Sunday | 2021-05-23 | 22:00 | 23:00 | 1:00 | Finalising and Submitting the Testing plan | Testing plan is part of the course assessment | The Testing plan was submitted before deadline
Monday | 2021-05-24 | 10:00 | 11:00 | 1:00 | Attending the 12th client meeting | We updated the client with the project progress and received their feedbacks. | To plan our tasks based on the client's feedbacks and demands. The client agreed that this is the last meeting.
Monday | 2021-05-24 | 11:00 | 11:30 | 0:30 | Attending the 35th internal team meeting | Right after the meeeting with the client, our mind was fresh and we were able to come up with the to-do list easily. | We managed to plan the tasks according to the client's feedbacks.
Monday | 2021-05-24 | 20:00 | 21:40 | 1:40 | Watching lectures of week 10 and week 11 | The lecture of week 10 gave me some ideas about how to design the UI/UX for the project and things we need to take note for the testing plan submission. The lecture of week 11 talked about the requirements of the poster, poster presentation and final report. | We need to follow the course coordinator's instructions for our assignment submission.
Monday | 2021-05-24 | 21:40 | 22:40 | 1:00 | Updating Github with the test cases as part of Testing plan submission | Together with the testing plan, which is part of the course assessment, we also need to submit the test cases conducted to GitHub | All the related test cases and instructions to execute the tests were submitted on time
Tuesday | 2021-05-25 | 10:00 | 16:00 | 6:00 | Writing the allocated sections of the user guide and technical specs | Technical specifications and user guide documents are the documentation that we have to deliver to the client in milestone 2 | To present the results to the team during the internal team meeting
Wednesday | 2021-05-26 | 22:00 | 22:30 | 0:30 | Attending the 36th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-29 | 10:00 | 18:00 | 8:00 | Finalising the user guide and completing the technical specs | Technical specifications and user guide documents are the documentation that we have to deliver to the client in milestone 2 | To present the results to the team during the internal team meeting
Saturday | 2021-05-29 | 19:00 | 22:00 | 3:00 | Studying how to prepare for the poster and Preparing a poster template | The poster is part of the course assessment | To discuss with the team during the internal team meeting about the task allocation for the poster
Saturday | 2021-05-29 | 22:00 | 22:45 | 0:45 | Attending the 37th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Saturday | 2021-05-29 | 23:15 | 0:15 | 1:00 | Preparing timesheet for week 11 and Uploading the timesheet to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | To prepare proposed timesheet for week 12
|  |  | Total | 26:40

## Week 12
MCI Project Weekly Time Sheet
Team | 3 | Student ID | a1801895 | Student Name | Nhu Quynh Hoa | Week starting: | 2021-05-30
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2021-05-31 | 15:00 | 16:00 | 1:00 | Watching lecture of week 12 | The lecture of week 12 gave me some ideas about the final assignments. | We need to follow the course coordinator's instructions for our final assignment submission.
Tuesday | 2021-06-01 | 10:00 | 12:00 | 2:00 | Revising the technical specifications | Technical specifications is the documentation that we have to deliver to the client in milestone 2 | Studying the technical specs helps me to understand the project more and prepare the poster better.
Tuesday | 2021-06-01 | 13:00 | 16:30 | 3:30 | Preparing the poster | The poster is part of the course assessment | To present the results to the team during the internal team meeting
Wednesday | 2021-06-02 | 22:00 | 23:00 | 1:00 | Attending the 38th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Thursday | 2021-06-03 | 13:00 | 16:00 | 3:00 | Revising the poster | The poster is part of the course assessment | To ask for feedbacks from team members before showing it to the course coordinator during the Q&A session
Friday | 2021-06-04 | 15:00 | 16:00 | 1:00 | Attending the Q&A session | The session is an opportunity for us to get feedbacks from the course coordinator about our poster | To revise the poster as per the course coordinator's feedbacks
Friday | 2021-06-04 | 19:00 | 22:00 | 3:00 | Revising the poster | The poster is part of the course assessment | To ask for feedbacks from team members
Saturday | 2021-06-05 | 10:00 | 18:00 | 8:00 | Preparing for the poster presentation | The poster presentation is part of the course assessment | Completed with the script for the presentation and practised presenting before the actual one
Saturday | 2021-06-05 | 22:00 | 23:00 | 1:00 | Attending the 39th internal team meeting | The meeting was when we updated the status of our assigned tasks and planned the tasks for the coming week. | Every member was on the same page about the project requirements and what to do next.
Sunday | 2021-06-06 | 11:00 | 15:00 | 4:00 | Video recording for poster presentation | The poster presentation is part of the course assessment | To finalise the recordings for the poster and final presentation submission
Sunday | 2021-06-06 | 15:00 | 16:00 | 1:00 | Preparing timesheet for week 12 and Individual summary as well as Uploading them to GitHub | When preparing the timesheet, I reflect on what I have and have not achieved during the week so that I can monitor my tasks more effectively to keep up with the project pace. | This is the last timesheet for the course
|  |  | Total | 28:30

## Calculation
Week | Hours
2 | 27
3 | 19
4 | 36.75
5 | 20.5
6 | 27
2-week mid-term break | 61.5
7 | 21.5
8 | 25
9 | 42.4167
10 | 40
11 | 26.67
12 | 28.5
Total | 375.8367
Average | 28.9105